## Slide 1
Group 6 – Book Buddi
Project Plan
1.20
Denampo, Elwison
Ralota, Marie Abigail

## Slide 2
Revision History
Rev No. | MODIFIED BY | MODIFIED DATE | REMARKS | PRELIMINARY REVIEW & APPROVAL | DATE REVIEWED | FINAL REVIEW & APPROVAL | DATE APPROVED
1.00 | Denampo, Elwison | 2025/08/23 | Initial Creation | Denampo, Elwison | 2025/08/23 | Ralota, Marie Abigail | yyyy/mm/dd
1.10 | Denampo, Elwison | 2025/11/12 | Revision of Team Composition, Control & Monitoring | Denampo, Elwison | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd
1.20 | Denampo, Elwison | 2025/11/17 | Updated the Man-Weeks | Denampo, Elwison | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd

## Slide 3
PROJECT INTRODUCTION

## Slide 4
Project Overview
GROUP NAME | Group 6
PROJECT NAME | Book Buddi
PROJECT CODE | N/A
CLIENT | ALLIANCE SOFTWARE, INC
BUSINESS UNIT | N/A
ACCOUNT CATEGORY | 
PROJECT TYPES | 
 | If others, please specify:
 | Note: For Multiple Enhancement/RFC and Ground Up, create a sub-Project Plan per Activity. For Production Support, refer to Project Monitoring Tool (ie. JIRA, Mantis, SugarCRM, Case Portal, Excel) for the Case Details.
PROCESS/ES FOLLOWED | 
HOLIDAY CALENDAR | 
PROJECT DESCRIPTION | This project is a web-based Library Management and Book Catalogue System designed for both general users and administrators. It features a comprehensive book catalogue with detailed information and robust search functionality. Users can borrow and return books, as well as place requests for titles. An Admin Panel, secured with authentication, provides tools for managing the catalogue including listing, adding, editing, and deleting books. The system also includes a Reporting Module, which generates reports on borrowing activity, inventory, members, book requests, and lost books. These reports support both system analytics and issue tracking. Additionally, the application incorporates a notification system, accessible via a dedicated page and a dropdown panel. Users will receive personalized notifications such as updates on book requests, due dates, and overdue returns.

## Slide 5
Project Development Environment

## Slide 6
Project Objectives
Programming Language
  Front-end : HTML, CSS, Razor
  Backend : C#
IDE : VS Code
DB : Microsoft SQL Server
Design Tools : Figma
3rd Party Apps/Libraries : Razor Component Library
Supported Browser
  Chrome : ✓
  Firefox : ✓
  Safari : ✗
  Internet Explorer : ✗
  Microsoft Edge : ✗
Supported Mobile Platforms
  Windows : ✓
  Mobile Responsive? : ✗
Screen Resolution : Responsive
Server Information
  Developer Server : SQL Server
  Staging / QA Server : NA
  Production Server : NA
Mode of Access : Internet

## Slide 7
Resource Capacity

## Slide 8
Team Composition
Role | Member | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
PROJECT MANAGER | Denampo, Elwison | 0.50 MD | 0.50 MD | 0.50 MD | 0.50 MD | 0.38 MD | 0.60 MW | 0.00 MD | 0.25 MW | 0.38 MD | 0.50 MD
TECHNICAL LEAD | Osorio, Raphael Chase | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.50 MW | 0.30 MW | 0.35 MW | 0.20 MW | 0.30 MW
DEVELOPERS (5) | Denampo, Elwison (BE + FE) | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.40 MW | 0.80 MW | 0.70 MW | 0.60 MW | 1.00 MW
 | Osorio, Raphael Chase (BE + FE) | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.40 MW | 0.80 MW | 0.65 MW | 0.60 MW | 0.75 MW
 | Rivera, Marc Gerard | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.40 MW | 0.75 MW | 0.65 MW | 0.50 MW | 0.30 MW
 | Siloy, Jaspher Lawrence | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.50 MW | 0.80 MW | 0.70 MW | 0.60 MW | 0.45 MW
 | Vega, Flexter | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.38 MD | 0.40 MW | 0.75 MW | 0.50 MW | 0.55 MW | 0.30 MW
QA (#) | Denampo, Elwison | 0.00 MW | 0.00 MW | 0.00 MW | 0.00 MW | 0.38 MD | 0.40 MW | 0.45 MW | 0.30 MW | 0.40 MW | 0.80 MW
 | Osorio, Raphael Chase | 0.00 MW | 0.00 MW | 0.00 MW | 0.00 MW | 0.38 MD | 0.30 MW | 0.40 MW | 0.30 MW | 0.45 MW | 0.35 MW
 | Rivera, Marc Gerard | 0.00 MW | 0.00 MW | 0.00 MW | 0.00 MW | 0.38 MD | 0.20 MW | 0.50 MW | 0.20 MW | 0.30 MW | 0.30 MW
 | Siloy, Jaspher Lawrence | 0.00 MW | 0.00 MW | 0.00 MW | 0.00 MW | 0.38 MD | 0.30 MW | 0.35 MW | 0.25 MW | 0.35 MW | 0.40 MW
 | Vega, Flexter | 0.00 MW | 0.00 MW | 0.00 MW | 0.00 MW | 0.38 MD | 0.20 MW | 0.45 MW | 0.20 MW | 0.35 MW | 0.35 MW
1MW = 5DAYS; 1MD = 8HRS |  |  |  |  |  |  |  |  |  |  | 
If Project is time & material- indicate monthly billed headcount
If Project is Project-based - indicate total estimate breakdown
ACTIVE MEMBERS
YEAR: 2025
Legend: B – Billed, IB – Internal Billed, S – Support

## Slide 9
Risk Management

## Slide 10
Risk Analysis
Risk | Probability | Consequence | Prevention | Mitigation
Skill Gap in C# | High | Slower development, more bugs, confusion with syntax | Watch tutorials, read documentation | Ask guidance from professor/peers, use online forums
Database Connection Problems | Medium | Catalogue won’t load or update properly, or even connect at all | Test database connection early, use sample data first | Keep backup database, simplify queries if errors occur
Version Control Conflicts | Medium | Code overwritten or lost when merging | Use Git branches properly, communicate before pushing code, make use of Pull Requests in GitHub | Keep a stable backup branch, redo only the latest changes
Unclear Error Messages Between Layers | Medium | Team struggles to debug because frontend only shows “Error” with no details. | Implement logging in backend for DB queries and API calls. | Use try-catch blocks with simple user-friendly messages.
Authentication Flow Breaks | Medium | Users can’t log in or session doesn’t persist. | Implement a very simple login system first (admin/student roles) | Add a longer and persistent session time with token refresh and proper redirecting

## Slide 11
Control & Monitoring

## Slide 12
Control & Monitoring
PROJECT TOOLS | 
Project Management Tool / Project Tracker | N/A
Code Management | Git, Github
Bug Tracking System | N/A
Project Tracker – indicate what will be the project tracker tools with the corresponding links.
Code Management – indicate what will be the code repository tool and its link.
Bug Tracking System – indicate how to track bugs. Indicated link when necessary.
Daily Time Record – Indicate DTR Project Name

## Slide 13
Control & Monitoring
PROJECT TEMPLATES |  | 
Document | Template (File Name) | Actual File (Naming Convention)
Meeting Minutes | N/A | N/A
Review Minutes | N/A | N/A
HLD | Alliance Low Code Program_HLD_[Group_Number]_[Application_Name].pptx | Alliance Low Code Program_HLD_G6_BookBuddi.pptx
LLD | N/A | N/A
Unit Test Cases | N/A | N/A
Unit Test Results | N/A | N/A
WBS | WBS_(Account Name)_(Application Name)_yyyymmdd.xlsx | WBS_G6_BookBuddi.xlsx
Row may be added/removed depending on the project milestones / activities.

## Slide 14
Schedule

## Slide 15
Project Schedule
Please refer to the WBS document.

## Slide 17
Alliance Software Incorporated
jobs@alliance.com.ph
+63 (032) 231 4219
238 6595
www.alliance.com.ph