## Cover
Group 6 - BookBuddi
BookBuddi
WBS Estimate
Revision No. : | 1.4
Modified By – Date : | Denampo, Elwison - 2025/11/17
Preliminary Review and Approval – Date : | Last Name, First Name - yyyy/mm/dd
Final Review and Approval – Date : | Last Name, First Name - yyyy/mm/dd

## Revision History
|  | REVISION HISTORY |  | REVISION HISTORY
REV NO | MODIFIED BY |  | MODIFIED DATE |  | REMARKS | PRELIMINARY REVIEW AND APPROVAL | DATE REVIEWED | FINAL REVIEW AND APPROVAL | DATE APPROVED
1 | Denampo, Elwison |  | 2025-08-23 |  | Initial Creation | Last Name, First Name | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd
1.1 | Denampo, Elwison |  | 2025-11-12 |  | Addition of Cover, Revision History, Function List | Last Name, First Name | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd
1.2 | Denampo, Elwison |  | 2025-11-13 |  | Revision of Jumpstart Progam Schedule | Last Name, First Name | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd
Rivera, Marc Gerard
1.3 | Denampo, Elwison |  | 2025-11-15 |  | Revision of Function List (Added entries) | Last Name, First Name | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd
1.4 | Denampo, Elwison |  | 2025-11-17 |  | Revision of Jumpstart Progam Schedule, and Function List | Last Name, First Name | yyyy/mm/dd | Last Name, First Name | yyyy/mm/dd

## Function List
WBS Reference | MODULE | FUNCTION / DESCRIPTION / ASSUMPTIONS | Type |  | Estimate (MD) | Remarks
13 | LANDING PAGE |  |  |  | 5
|  | The main entry point of the system that introduces users to the library catalogue and provides access to login, registration, and book search functions. | Web
15 | AUTHENTICATION |  |  |  | 5
16 | LOGIN PAGE | Allows users to securely log into their accounts using their registered credentials with authentication via email | Web |  | 3
20 | REGISTER/SIGNUP | Allows users to securely register their credentials to have stored in the database with additional authentication via email. | Web |  | 1
25 | FORGOT PASSWORD | Allows users to recover their accounts and reset/change their passwords via their registered email | Web |  | 4
31 | BOOK CATALOGUE |  |  |  | 7
32 | LIST | Displays a paginated list or grid of all available books in the public catalog. | Web |  | 5
37 | VIEW | Displays the full, detailed page for a single book when selected from the list. | Web |  | 5
42 | SEARCH | Implements the backend logic to filter the book list based on user queries (title, author, genre). | Web |  | 2
46 | BORROWING SYSTEM |  |  |  | 8
32 | LIST | Displays the list of books currently borrowed by the logged-in user, including due dates. | Web |  | 5
51 | ADD (Borrow Book) | Implements the function for a user to check out an available book and adds a new record to their borrowing history. | Web |  | 1
57 | EDIT (Return Book) | Implements the function for a user to return a borrowed book, updating its status to "available". | Web |  | 1
63 | VIEW (History) | Displays a read-only list of all past books the user has borrowed and returned. | Web |  | 3
67 | REQUEST | Provides a form for users to request a new book title that is not in the catalog. | Web |  | 5
72 | NOTIFICATIONS (User-Facing) |  |  |  | 3
73 | Notification Dropdown | The "bell" icon or list showing recent, unread notifications. | Web |  | 1
77 | Notification Page | A dedicated page showing all of the user's past and present notifications. | Web |  | 1
80 | ADMIN PANEL |  |  |  | 6
81 | LOGIN | Allows specific admin accounts to securely log in using their registered (or provided) credentials | Web |  | 2
85 | DASHBOARD | The admin's main homepage showing key statistics and summaries. | Web |  | 2
89 | USER MANAGEMENT | Allows the admin to manage users/members registered in the catalogue. | Web |  | 2
90 | LIST | Displays a paginated and searchable list of all registered users in the system. | Web |  | 5
94 | ADD | Provides an admin form to manually create a new user account. | Web |  | 2
98 | EDIT | Provides an admin form to modify an existing user's details (e.g., reset password, change role). | Web |  | 2
102 | DELETE | Implements the function for an admin to deactivate or permanently remove a user account. | Web |  | 2
106 | VIEW | Displays a read-only page showing the full profile and borrowing history of a single user. | Web |  | 5
110 | BOOK MANAGEMENT | Allows the admin to manage books in the catalogue. | Web |  | 2
111 | LIST | Displays a paginated and searchable list of all books in the database (both available and borrowed). | Web |  | 5
115 | ADD | Provides an admin form to add a new book to the catalog, including its title, author, and cover image. | Web |  | 2
120 | EDIT | Provides an admin form to modify an existing book's details (e.g., update description, change ISBN). | Web |  | 2
124 | DELETE | Implements the function for an admin to permanently remove a book from the catalog. | Web |  | 2
128 | VIEW | Displays a read-only page showing the full details and borrowing history for a single book. | Web |  | 5
132 | CATEGORY MANAGEMENT | Allows the admin to manage book genres/categories (e.g., 'Fiction', 'Sci-Fi') in the catalogue. | Web |  | 2
133 | LIST | Displays a list of all book categories/genres. | Web |  | 5
136 | ADD | Provides a form or input to create a new book category. | Web |  | 2
140 | EDIT | Implements the function to rename an existing category. | Web |  | 2
143 | DELETE | Implements the function to remove an existing category. | Web |  | 2
146 | REPORTING | Generate and view data summaries for the application. | Web |  | 2
147 | Borrowing Report | Generates a report on book borrowing trends (e.g., most popular books, peak times). | Web |  | 2
152 | Inventory Report | Generates a report summarizing all books, including total copies, available, and checked out. | Web |  | 2
156 | Member Report | Generates a report on user activity (e.g., new signups, active vs. inactive users). | Web |  | 2
160 | Request Report | Displays a queue of all user-submitted book requests, with options to approve or reject them. | Web |  | 2
164 | Lost Book Report | Generates a report to track books that have been marked as "Lost" or are severely overdue. | Web |  | 2
168 | NOTIFICATIONS (Admin Config) | Generate and view data summaries for the application. | Web |  | 2
169 | Configure Email Notifications | A settings page to input the email server (SMTP) credentials for sending emails. | Web |  | 2
170 | Implement Due Date Reminders | Create the automated job (cron job) that runs daily to find and send overdue book reminders. | Web |  | 2
171 | QUALITY ASSURANCE |  |  |  | 18
172 | Manual Testing |  |  |  | 18
173 | Testing UI Responsiveness | Check that the application looks and functions correctly on different screen sizes (desktop, tablet, mobile). | Web |  | 18
174 | Testing Authentication Flow | Attempt to log in, register, reset password, and log out with valid and invalid data. | Web |  | 16
175 | Testing Book Catalog | Verify that searching, filtering, and viewing books works perfectly. | Web |  | 14
176 | Testing Borrowing System | Go through the full user story of borrowing a book, seeing it on the dashboard, and returning it. | Web |  | 9
177 | Testing Admin Features | Verify that all admin CRUD functions work and that security is enforced (a normal user cannot access the admin panel). | Web |  | 7
Overall
|  |  | MD | 132
|  |  | MM | 6.6

## Jumpstart Program Schedule
Denampo, Elwison | Osorio, Raphael | Siloy, Jaspher Lawrence | Vega, Flexter | Rivera, Marc Gerard | WBS | Task | Baseline Start | Baseline End | Days | Predecessors | Actual Days Data | Actual Start | Actual End
x | x | x | x | x | 1 | PROJECT MANAGEMENT | 2025-08-23 | 2025-11-20 | 88 | - | 88 | 2025-08-23 | 2025-11-20
x | x | x | x | x | 2 | Creation of Project Plan | 2025-08-23 | 2025-08-30 | 8 | - | 8 | 2025-08-23 | 2025-08-30
x | x | x | x | x | 3 | Creation of WBS | 2025-08-23 | 2025-08-30 | 8 | 2 | 8 | 2025-08-23 | 2025-08-30
x | x | x | x | x | 4 | Creation of HLD | 2025-08-23 | 2025-11-17 | 85 | 3 | 85 | 2025-08-23 | 2025-11-17
x | x | x | x | x | 5 | PROJECT STRUCTURE | 2025-08-23 | 2025-11-08 | 76 | 4 | 76 | 2025-08-23 | 2025-11-08
| x | x |  |  | 6 | Figma Wireframe | 2025-09-13 | 2025-09-15 | 3 | 5 | 3 | 2025-09-13 | 2025-09-15
| x | x |  |  | 7 | Color Palette Selection and Logo | 2025-09-13 | 2025-09-18 | 6 | 6 | 6 | 2025-09-13 | 2025-09-18
| x | x |  |  | 8 | Finding References | 2025-09-13 | 2025-09-14 | 2 | 7 | 2 | 2025-09-13 | 2025-09-14
x |  |  |  |  | 9 | ERD Creation | 2025-09-14 | 2025-09-18 | 5 | 8 | 5 | 2025-09-14 | 2025-09-18
x |  |  |  |  | 10 | Initialization of Database | 2025-09-20 | 2025-09-23 | 4 | 9 | 4 | 2025-09-20 | 2025-09-23
x |  |  |  |  | 11 | Project Hierarchy | 2025-09-20 | 2025-09-23 | 4 | 10 | 4 | 2025-09-20 | 2025-09-23
x | x | x | x | x | 12 | DEVELOPMENT | 2025-09-20 | 2025-11-20 | 61 | 11 | 61 | 2025-09-20 | 2025-11-20
| x | x |  |  | 13 | LANDING PAGE | 2025-09-20 | 2025-09-24 | 5 | 12 | 5 | 2025-09-20 | 2025-09-24
| x | x |  |  | 14 | Creating of Landing Page (Frontend) | 2025-09-20 | 2025-09-24 | 5 | 13 | 5 | 2025-09-20 | 2025-09-24
x | x | x | x | x | 15 | AUTHENTICATION | 2025-09-20 | 2025-09-24 | 5 | 14 | 5 | 2025-09-20 | 2025-09-24
x | x | x |  |  | 16 | LOGIN PAGE | 2025-09-21 | 2025-09-23 | 3 | 15 | 3 | 2025-09-21 | 2025-09-23
| x | x |  |  | 17 | Design and Implement Frontend | 2025-09-21 | 2025-09-24 | 4 | 16 | 4 | 2025-09-21 | 2025-09-24
x |  |  |  |  | 18 | Configure Authentication from Backend | 2025-09-17 | 2025-09-26 | 10 | 17 | 10 | 2025-09-17 | 2025-09-26
x |  |  | x | x | 19 | Validate and Connect Frontend with Backend | 2025-09-17 | 2025-09-17 | 1 | 18 | 1 | 2025-09-17 | 2025-09-17
x | x | x | x | x | 20 | REGISTER/SIGNUP | 2025-09-17 | 2025-09-17 | 1 | 19 | 1 | 2025-09-17 | 2025-09-17
| x | x |  |  | 21 | Design and Implement Frontend | 2025-09-17 | 2025-09-22 | 6 | 20 | 6 | 2025-09-17 | 2025-09-22
x |  |  |  |  | 22 | Configure Authentication from Backend | 2025-09-17 | 2025-09-22 | 6 | 21 | 6 | 2025-09-17 | 2025-09-22
x |  |  | x | x | 23 | Validate and Connect Frontend with Backend | 2025-09-17 | 2025-09-24 | 8 | 22 | 8 | 2025-09-17 | 2025-09-24
x |  |  |  |  | 24 | Insert on new data on the database | 2025-09-26 | 2025-10-04 | 9 | 23 | 9 | 2025-09-26 | 2025-10-04
x | x | x | x | x | 25 | FORGOT PASSWORD | 2025-09-28 | 2025-10-01 | 4 | 24 | 4 | 2025-09-28 | 2025-10-01
| x | x |  |  | 26 | Design and Implement Frontend | 2025-09-26 | 2025-09-28 | 3 | 25 | 3 | 2025-09-26 | 2025-09-28
x |  |  |  |  | 27 | Configure Authentication from Backend | 2025-09-28 | 2025-09-29 | 2 | 26 | 2 | 2025-09-28 | 2025-09-29
x |  |  | x | x | 28 | Validate and Connect Frontend with Backend | 2025-09-29 | 2025-10-03 | 5 | 27 | 5 | 2025-09-29 | 2025-10-03
x |  |  |  |  | 29 | Validate token and Input for New Password | 2025-09-29 | 2025-10-04 | 6 | 28 | 6 | 2025-09-29 | 2025-10-04
x |  |  |  |  | 30 | Update User Password | 2025-10-04 | 2025-10-05 | 2 | 29 | 2 | 2025-10-04 | 2025-10-05
x | x | x | x | x | 31 | BOOK CATALOGUE | 2025-10-06 | 2025-10-12 | 7 | 30 | 7 | 2025-10-06 | 2025-10-12
x | x | x | x | x | 32 | LIST | 2025-10-06 | 2025-10-10 | 5 | 31 | 5 | 2025-10-06 | 2025-10-10
| x | x |  | x | 33 | Design and Implement Frontend | 2025-10-06 | 2025-10-06 | 1 | 32 | 1 | 2025-10-06 | 2025-10-06
x |  |  |  |  | 34 | Fetch and display all books from database | 2025-10-06 | 2025-10-06 | 1 | 33 | 1 | 2025-10-06 | 2025-10-06
|  |  | x |  | 35 | Implement Search Bar with Filters | 2025-10-08 | 2025-10-10 | 3 | 34 | 3 | 2025-10-08 | 2025-10-10
x |  |  |  |  | 36 | Implement Pagination | 2025-10-07 | 2025-10-07 | 1 | 35 | 1 | 2025-10-07 | 2025-10-07
x | x | x |  | x | 37 | VIEW | 2025-10-06 | 2025-10-10 | 5 | 36 | 5 | 2025-10-06 | 2025-10-10
| x | x |  | x | 38 | Design and Implement Frontend | 2025-10-06 | 2025-10-06 | 1 | 37 | 1 | 2025-10-06 | 2025-10-06
x |  |  |  |  | 39 | Fetch and display full book details | 2025-10-06 | 2025-10-06 | 1 | 38 | 1 | 2025-10-06 | 2025-10-06
x | x | x |  |  | 40 | Show Availability Status | 2025-10-06 | 2025-10-06 | 1 | 39 | 1 | 2025-10-06 | 2025-10-06
x | x | x |  |  | 41 | Display Related Books | 2025-10-08 | 2025-10-08 | 1 | 40 | 1 | 2025-10-08 | 2025-10-08
| x | x | x | x | 42 | SEARCH | 2025-10-09 | 2025-10-10 | 2 | 41 | 2 | 2025-10-09 | 2025-10-10
| x | x |  | x | 43 | Design and Implement Search Bar | 2025-10-09 | 2025-10-10 | 2 | 42 | 2 | 2025-10-09 | 2025-10-10
x |  |  | x |  | 44 | Implement search and filtering from backend | 2025-10-09 | 2025-10-10 | 2 | 43 | 2 | 2025-10-09 | 2025-10-10
| x |  |  |  | 45 | "Filter by Title, Author, Genre, ISBN" | 2025-10-10 | 2025-10-12 | 3 | 44 | 3 | 2025-10-10 | 2025-10-12
| x | x |  |  | 46 | BORROWING SYSTEM | 2025-10-13 | 2025-10-20 | 8 | 45 | 8 | 2025-10-13 | 2025-10-20
| x | x |  | x | 47 | LIST | 2025-10-13 | 2025-10-13 | 1 | 46 | 1 | 2025-10-13 | 2025-10-13
| x | x |  | x | 48 | Design and Implement Frontend | 2025-10-13 | 2025-10-13 | 1 | 47 | 1 | 2025-10-13 | 2025-10-13
x |  |  |  |  | 49 | Fetch and display borrowed books | 2025-10-13 | 2025-10-13 | 1 | 48 | 1 | 2025-10-13 | 2025-10-13
x |  |  |  |  | 50 | Display due dates and status | 2025-10-13 | 2025-10-13 | 1 | 49 | 1 | 2025-10-13 | 2025-10-13
x | x | x |  | x | 51 | ADD (Borrow Book) | 2025-10-14 | 2025-10-14 | 1 | 50 | 1 | 2025-10-14 | 2025-10-14
| x | x |  | x | 52 | Design and Implement Frontend | 2025-10-14 | 2025-10-14 | 1 | 51 | 1 | 2025-10-14 | 2025-10-14
x |  |  |  |  | 53 | Configure Borrowing Logic from Backend | 2025-10-14 | 2025-10-14 | 1 | 52 | 1 | 2025-10-14 | 2025-10-14
x |  |  |  |  | 54 | Validate Book Availability | 2025-10-14 | 2025-10-14 | 1 | 53 | 1 | 2025-10-14 | 2025-10-14
x |  |  |  |  | 55 | Insert Borrowing Record in Database | 2025-10-14 | 2025-10-14 | 1 | 54 | 1 | 2025-10-14 | 2025-10-14
[5 empty] | 56 | Send Confirmation Notification | 2025-10-14 | 2025-10-14 | 1 | 55 | 1 | 2025-10-14 | 2025-10-14
x | x | x |  | x | 57 | EDIT (Return Book) | 2025-10-14 | 2025-10-14 | 1 | 56 | 1 | 2025-10-14 | 2025-10-14
| x | x |  | x | 58 | Design and Implement Frontend | 2025-10-14 | 2025-10-14 | 1 | 57 | 1 | 2025-10-14 | 2025-10-14
x |  |  |  |  | 59 | Configure Return Logic from Backend | 2025-10-14 | 2025-10-14 | 1 | 58 | 1 | 2025-10-14 | 2025-10-14 | S
x |  |  |  |  | 60 | Update Book Availability Status | 2025-10-14 | 2025-10-14 | 1 | 59 | 1 | 2025-10-14 | 2025-10-14
x |  |  |  |  | 61 | Calculate Late Fees if applicable | 2025-10-14 | 2025-10-15 | 2 | 60 | 2 | 2025-10-14 | 2025-10-15
x |  |  |  |  | 62 | Update Borrowing Record | 2025-10-14 | 2025-10-15 | 2 | 61 | 2 | 2025-10-14 | 2025-10-15
| x | x |  | x | 63 | VIEW (History) | 2025-10-15 | 2025-10-17 | 3 | 62 | 3 | 2025-10-15 | 2025-10-17
| x | x |  | x | 64 | Design and Implement Frontend | 2025-10-15 | 2025-10-15 | 1 | 63 | 1 | 2025-10-15 | 2025-10-15
x | x |  |  |  | 65 | Fetch User's Borrowing Records | 2025-10-15 | 2025-10-16 | 2 | 64 | 2 | 2025-10-15 | 2025-10-16
x | x |  |  |  | 66 | Display Current and Past Borrowings | 2025-10-15 | 2025-10-17 | 3 | 65 | 3 | 2025-10-15 | 2025-10-17
x | x | x |  |  | 67 | REQUEST | 2025-10-15 | 2025-10-19 | 5 | 66 | 5 | 2025-10-15 | 2025-10-19
| x | x |  |  | 68 | Design and Implement Frontend | 2025-10-15 | 2025-10-15 | 1 | 67 | 1 | 2025-10-15 | 2025-10-15
x |  |  |  |  | 69 | Configure Request Logic from Backend | 2025-10-15 | 2025-10-17 | 3 | 68 | 3 | 2025-10-15 | 2025-10-17
x |  |  |  |  | 70 | Insert Book Request in Database | 2025-10-17 | 2025-10-18 | 2 | 69 | 2 | 2025-10-17 | 2025-10-18
x |  |  |  |  | 71 | Notify Admin of New Request | 2025-10-18 | 2025-10-19 | 2 | 70 | 2 | 2025-10-18 | 2025-10-19
| x | x |  | x | 72 | NOTIFICATIONS (User-Facing) | 2025-10-19 | 2025-10-21 | 3 | 71 | 3 | 2025-10-19 | 2025-10-21
| x | x |  | x | 73 | Notification Dropdown | 2025-10-19 | 2025-10-19 | 1 | 72 | 1 | 2025-10-19 | 2025-10-19
| x | x |  | x | 74 | Design and Implement Frontend | 2025-10-19 | 2025-10-19 | 1 | 73 | 1 | 2025-10-19 | 2025-10-19
| x |  |  |  | 75 | Fetch Real-time Notifications | 2025-10-19 | 2025-10-19 | 1 | 74 | 1 | 2025-10-19 | 2025-10-19
| x |  |  |  | 76 | Mark as Read Functionality | 2025-10-20 | 2025-10-21 | 2 | 75 | 2 | 2025-10-20 | 2025-10-21
| x | x |  | x | 77 | Notification Page | 2025-10-19 | 2025-10-19 | 1 | 76 | 1 | 2025-10-19 | 2025-10-19
| x | x |  | x | 78 | Design and Implement Frontend | 2025-10-19 | 2025-10-19 | 1 | 77 | 1 | 2025-10-19 | 2025-10-19
| x | x |  |  | 79 | Display All Notifications | 2025-10-19 | 2025-10-19 | 1 | 78 | 1 | 2025-10-19 | 2025-10-19
x |  |  |  | x | 80 | ADMIN PANEL | 2025-10-21 | 2025-10-26 | 6 | 79 | 6 | 2025-10-21 | 2025-10-26
x |  |  |  | x | 81 | LOGIN | 2025-10-21 | 2025-10-22 | 2 | 80 | 2 | 2025-10-21 | 2025-10-22
| x | x |  | x | 82 | Design and Implement Admin Login | 2025-10-21 | 2025-10-22 | 2 | 81 | 2 | 2025-10-21 | 2025-10-22
x |  |  |  |  | 83 | Configure Admin Authentication | 2025-10-21 | 2025-10-22 | 2 | 82 | 2 | 2025-10-21 | 2025-10-22
x |  |  |  |  | 84 | Implement Role-Based Access Control | 2025-10-21 | 2025-10-22 | 2 | 83 | 2 | 2025-10-21 | 2025-10-22
x | x | x |  |  | 85 | DASHBOARD | 2025-10-21 | 2025-10-22 | 2 | 84 | 2 | 2025-10-21 | 2025-10-22
| x | x |  |  | 86 | Design and Implement Dashboard | 2025-10-21 | 2025-10-22 | 2 | 85 | 2 | 2025-10-21 | 2025-10-22
[5 empty] | 87 | Display statistics and analytics | 2025-10-21 | 2025-10-22 | 2 | 86 | 2 | 2025-10-21 | 2025-10-22
[5 empty] | 88 | Show recent activities | 2025-10-21 | 2025-10-22 | 2 | 87 | 2 | 2025-10-21 | 2025-10-22
x | x | x |  | x | 89 | USER MANAGEMENT | 2025-10-22 | 2025-10-23 | 2 | 88 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  | x | 90 | LIST | 2025-10-22 | 2025-10-23 | 2 | 89 | 2 | 2025-10-22 | 2025-10-23
| x | x |  | x | 91 | Design and Implement Frontend | 2025-10-22 | 2025-10-23 | 2 | 90 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 92 | Fetch all users from database | 2025-10-22 | 2025-10-23 | 2 | 91 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 93 | Display user information and status | 2025-10-22 | 2025-10-23 | 2 | 92 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  | x | 94 | ADD | 2025-10-22 | 2025-10-23 | 2 | 93 | 2 | 2025-10-22 | 2025-10-23
| x | x |  | x | 95 | Design and Implement Frontend | 2025-10-22 | 2025-10-23 | 2 | 94 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 96 | Validate user information | 2025-10-22 | 2025-10-23 | 2 | 95 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 97 | Insert new user in database | 2025-10-22 | 2025-10-23 | 2 | 96 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  | x | 98 | EDIT | 2025-10-22 | 2025-10-23 | 2 | 97 | 2 | 2025-10-22 | 2025-10-23
| x | x |  | x | 99 | Design and Implement Frontend | 2025-10-22 | 2025-10-23 | 2 | 98 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 100 | Fetch user data | 2025-10-22 | 2025-10-23 | 2 | 99 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 101 | Update user information in database | 2025-10-22 | 2025-10-23 | 2 | 100 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  |  | 102 | DELETE | 2025-10-22 | 2025-10-23 | 2 | 101 | 2 | 2025-10-22 | 2025-10-23
| x | x |  |  | 103 | Design and Implement Frontend | 2025-10-22 | 2025-10-23 | 2 | 102 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 104 | Implement confirmation dialog | 2025-10-22 | 2025-10-23 | 2 | 103 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 105 | Delete or deactivate user | 2025-10-22 | 2025-10-23 | 2 | 104 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  | x | 106 | VIEW | 2025-10-22 | 2025-10-23 | 2 | 105 | 2 | 2025-10-22 | 2025-10-23
| x | x |  | x | 107 | Design and Implement Frontend | 2025-10-22 | 2025-10-23 | 2 | 106 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 108 | Display full user details | 2025-10-22 | 2025-10-23 | 2 | 107 | 2 | 2025-10-22 | 2025-10-23
x |  |  |  |  | 109 | Show borrowing history | 2025-10-22 | 2025-10-23 | 2 | 108 | 2 | 2025-10-22 | 2025-10-23
x | x | x |  | x | 110 | BOOK MANAGEMENT | 2025-10-23 | 2025-10-24 | 2 | 109 | 2 | 2025-10-23 | 2025-10-24
x | x | x | x | x | 111 | LIST | 2025-10-23 | 2025-10-24 | 2 | 110 | 2 | 2025-10-23 | 2025-10-24
| x | x |  | x | 112 | Design and Implement Frontend | 2025-10-23 | 2025-10-24 | 2 | 111 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 113 | Fetch and Display all Books | 2025-10-23 | 2025-10-24 | 2 | 112 | 2 | 2025-10-23 | 2025-10-24
| x | x | x |  | 114 | Implement Search and Filter | 2025-10-23 | 2025-10-24 | 2 | 113 | 2 | 2025-10-23 | 2025-10-24
x | x | x |  | x | 115 | ADD | 2025-10-23 | 2025-10-24 | 2 | 114 | 2 | 2025-10-23 | 2025-10-24
| x | x |  | x | 116 | Design and Implement Frontend | 2025-10-23 | 2025-10-24 | 2 | 115 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 117 | Validate Book Information | 2025-10-23 | 2025-10-24 | 2 | 116 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 118 | Insert New Book in Database | 2025-10-23 | 2025-10-24 | 2 | 117 | 2 | 2025-10-23 | 2025-10-24
| x | x |  |  | 119 | Upload Book Cover Image | 2025-10-23 | 2025-10-24 | 2 | 118 | 2 | 2025-10-23 | 2025-10-24
x | x | x |  | x | 120 | EDIT | 2025-10-23 | 2025-10-24 | 2 | 119 | 2 | 2025-10-23 | 2025-10-24
| x | x |  | x | 121 | Design and Implement Frontend | 2025-10-23 | 2025-10-24 | 2 | 120 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 122 | Fetch Existing Book Data | 2025-10-23 | 2025-10-24 | 2 | 121 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 123 | Update Book Information in Database | 2025-10-23 | 2025-10-24 | 2 | 122 | 2 | 2025-10-23 | 2025-10-24
x | x | x |  |  | 124 | DELETE | 2025-10-23 | 2025-10-24 | 2 | 123 | 2 | 2025-10-23 | 2025-10-24
| x | x |  |  | 125 | Design and Implement Frontend | 2025-10-23 | 2025-10-24 | 2 | 124 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 126 | Implement confirmation dialog | 2025-10-23 | 2025-10-24 | 2 | 125 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 127 | Delete Book from Database | 2025-10-23 | 2025-10-24 | 2 | 126 | 2 | 2025-10-23 | 2025-10-24
x | x | x |  | x | 128 | VIEW | 2025-10-23 | 2025-10-24 | 2 | 127 | 2 | 2025-10-23 | 2025-10-24
| x | x |  | x | 129 | Design and Implement Frontend | 2025-10-23 | 2025-10-24 | 2 | 128 | 2 | 2025-10-23 | 2025-10-24
x |  |  |  |  | 130 | Fetch and display book details | 2025-10-23 | 2025-10-24 | 2 | 129 | 2 | 2025-10-23 | 2025-10-24
x | x | x |  |  | 131 | Show borrowing history for book | 2025-10-23 | 2025-10-24 | 2 | 130 | 2 | 2025-10-23 | 2025-10-24
| x | x |  | x | 132 | CATEGORY MANAGEMENT | 2025-10-24 | 2025-10-25 | 2 | 131 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 133 | LIST | 2025-10-24 | 2025-10-25 | 2 | 132 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 134 | Design and Implement Frontend | 2025-10-24 | 2025-10-25 | 2 | 133 | 2 | 2025-10-24 | 2025-10-25
x |  |  |  |  | 135 | Fetch and display all categories | 2025-10-24 | 2025-10-25 | 2 | 134 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 136 | ADD | 2025-10-24 | 2025-10-25 | 2 | 135 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 137 | Design and Implement Frontend | 2025-10-24 | 2025-10-25 | 2 | 136 | 2 | 2025-10-24 | 2025-10-25
x |  |  |  |  | 138 | Validate category information | 2025-10-24 | 2025-10-25 | 2 | 137 | 2 | 2025-10-24 | 2025-10-25
x |  |  |  |  | 139 | Insert category in database | 2025-10-24 | 2025-10-25 | 2 | 138 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 140 | EDIT | 2025-10-24 | 2025-10-25 | 2 | 139 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 141 | Design and Implement Frontend | 2025-10-24 | 2025-10-25 | 2 | 140 | 2 | 2025-10-24 | 2025-10-25
x |  |  |  |  | 142 | Update category in database | 2025-10-24 | 2025-10-25 | 2 | 141 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 143 | DELETE | 2025-10-24 | 2025-10-25 | 2 | 142 | 2 | 2025-10-24 | 2025-10-25
| x | x |  | x | 144 | Design and Implement Frontend | 2025-10-24 | 2025-10-25 | 2 | 143 | 2 | 2025-10-24 | 2025-10-25
x |  |  |  |  | 145 | Delete category from database | 2025-10-24 | 2025-10-25 | 2 | 144 | 2 | 2025-10-24 | 2025-10-25
x | x | x | x |  | 146 | REPORTING | 2025-10-25 | 2025-10-26 | 2 | 145 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x |  | 147 | Borrowing Report | 2025-10-25 | 2025-10-26 | 2 | 146 | 2 | 2025-10-25 | 2025-10-26
| x | x | x |  | 148 | Design and Implement Frontend | 2025-10-25 | 2025-10-26 | 2 | 147 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 149 | Fetch Borrowing Statistics | 2025-10-25 | 2025-10-26 | 2 | 148 | 2 | 2025-10-25 | 2025-10-26
|  |  | x |  | 150 | Generate Charts and Graphs | 2025-10-25 | 2025-10-26 | 2 | 149 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 151 | Export Report to PDF | 2025-10-25 | 2025-10-26 | 2 | 150 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x |  | 152 | Inventory Report | 2025-10-25 | 2025-10-26 | 2 | 151 | 2 | 2025-10-25 | 2025-10-26
| x | x | x |  | 153 | Design and Implement Frontend | 2025-10-25 | 2025-10-26 | 2 | 152 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 154 | Fetch Book Inventory Data | 2025-10-25 | 2025-10-26 | 2 | 153 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 155 | Display Available vs Borrowed Books | 2025-10-25 | 2025-10-26 | 2 | 154 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x |  | 156 | Member Report | 2025-10-25 | 2025-10-26 | 2 | 155 | 2 | 2025-10-25 | 2025-10-26
| x | x | x |  | 157 | Design and Implement Frontend | 2025-10-25 | 2025-10-26 | 2 | 156 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 158 | Fetch Member Statistics | 2025-10-25 | 2025-10-26 | 2 | 157 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 159 | Display Active vs Inactive Members | 2025-10-25 | 2025-10-26 | 2 | 158 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x |  | 160 | Request Report | 2025-10-25 | 2025-10-26 | 2 | 159 | 2 | 2025-10-25 | 2025-10-26
| x | x | x |  | 161 | Design and Implement Frontend | 2025-10-25 | 2025-10-26 | 2 | 160 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 162 | Fetch Book Request Data | 2025-10-25 | 2025-10-26 | 2 | 161 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 163 | Display Pending and Fulfilled Requests | 2025-10-25 | 2025-10-26 | 2 | 162 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x |  | 164 | Lost Book Report | 2025-10-25 | 2025-10-26 | 2 | 163 | 2 | 2025-10-25 | 2025-10-26
| x | x | x |  | 165 | Design and Implement Frontend | 2025-10-25 | 2025-10-26 | 2 | 164 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 166 | Fetch Lost Book Records | 2025-10-25 | 2025-10-26 | 2 | 165 | 2 | 2025-10-25 | 2025-10-26
x |  |  | x |  | 167 | Calculate Financial Impact | 2025-10-25 | 2025-10-26 | 2 | 166 | 2 | 2025-10-25 | 2025-10-26
x | x | x |  |  | 168 | NOTIFICATIONS (Admin Config) | 2025-10-25 | 2025-10-26 | 2 | 167 | 2 | 2025-10-25 | 2025-10-26
x |  |  |  |  | 169 | Configure Email Notifications | 2025-10-25 | 2025-10-26 | 2 | 168 | 2 | 2025-10-25 | 2025-10-26
x |  |  |  |  | 170 | Implement Due Date Reminders | 2025-10-25 | 2025-10-26 | 2 | 169 | 2 | 2025-10-25 | 2025-10-26
x | x | x | x | x | 171 | QUALITY ASSURANCE | 2025-11-03 | 2025-11-20 | 18 | 170 | 18 | 2025-11-03 | 2025-11-20
x | x | x | x | x | 172 | Manual Testing | 2025-11-03 | 2025-11-20 | 18 | 171 | 18 | 2025-11-03 | 2025-11-20
x | x | x | x | x | 173 | Testing UI Responsiveness | 2025-11-03 | 2025-11-20 | 18 | 172 | 18 | 2025-11-03 | 2025-11-20
x | x | x | x | x | 174 | Testing Authentication Flow | 2025-11-05 | 2025-11-20 | 16 | 173 | 16 | 2025-11-05 | 2025-11-20
x | x | x | x | x | 175 | Testing Book Catalog | 2025-11-07 | 2025-11-20 | 14 | 174 | 14 | 2025-11-07 | 2025-11-20
x | x | x | x | x | 176 | Testing Borrowing System | 2025-11-12 | 2025-11-20 | 9 | 175 | 9 | 2025-11-12 | 2025-11-20
x | x | x | x | x | 177 | Testing Admin Features | 2025-11-14 | 2025-11-20 | 7 | 176 | 7 | 2025-11-14 | 2025-11-20
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Complete Actual Start and Actual End columns
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Other sheets are missing? Cover Page Revision History Function List Reply: Resolved
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Complete assignment of Tasks Reply: Resolved